## UC
Time spent on use cases
Project: Perfect Time - Plan Your Trip |  | YouTrack Report: |  |  |  | Original file (without time spent updates for 1st semester UCs):
TINF17B2 |  | https://perfecttime.myjetbrains.com/youtrack/reports/time/145-1 |  |  |  | https://drive.google.com/open?id=1ZQ_V2uwXbj0vQeNRhskU6kZrGtW4QiVQ
TIME SPENT (ACTUAL)
UC | Documentation | Coding | Testing | Warm-Up time | Total | FP | Completed? | Remarks | Spalte1
UC Register / Login | 6 | 5 | 3 | 5 | 19 | 29.44 | TRUE
UC CRUD trips | 11 | 24 | 2 | 7 | 44 | 98.91 | TRUE | (view all trips and CRUD trips are separat use cases, but tasks often affect both, which is why they are put together for time evaluation)
UC CRUD locations | 8 | 40 | 6 | 38 | 92 | 75.44 | TRUE | (add and edit are separat use cases, but tasks often do affect both, which is why they are put together for time evaluation) | some time of locations (e.g. image upload) affected activity and therefor was split
UC CRUD activities | 3 | 28 | 4 | 15 | 50 | 75.44 | TRUE | (add and edit are separat use cases, but tasks often do affect both, which is why they are put together for time evaluation)
UC User Management | 4 | 50 | 5 | 15 | 74 | 42.32 | TRUE | (includes AuthZ and Follow Actions)
UC Export | 2 | 5 | 2 | 0 | 9 | 34.2 | TRUE | to JSON not ical
UC Copy Trip | 4 | 6 | 2 | 1 | 13 | 34.2 | TRUE
| 38 | 158 | 24 | 81 | 301
Time-FP-Evaluation
UC | FP | Time Total (/wo warm-up) | Time/FP
UC Register / Login | 29.44 | 14 | 0.47554
UC CRUD trips | 98.91 | 37 | 0.37408
UC CRUD locations | 75.44 | 54 | 0.7158
UC CRUD activities | 75.44 | 35 | 0.46394
Total Semester 1 | 279.23 | 140 | 0.50138
Schätzungen | FP | Time (estimated) | Time spent
UC User Management | 42.32 | 20.2211 | 74
UC Export | 34.2 | 18.144 | 9
UC Copy Trip | 34.2 | 18.144 | 13
Total Semester 2 | 110.72 | 56.509 | 96
Buffer: | 2.5 | 141.2724 | OK