## UC
Time spent on use cases
Project: Perfect Time - Plan Your Trip |  | YouTrack Report:
TINF17B2 |  | https://perfecttime.myjetbrains.com/youtrack/reports/time/145-1
UC | Documentation | Coding | Testing | Warm-Up time | Total | FP | Completed? | Remarks
UC Register / Login | 6 | 5 | 2 | 2 | 15 |  | TRUE
UC CRUD trips | 12 | 12 | 3 | 5 | 32 |  | FALSE
UC CRUD locations | 8 | 32 | 6 | 28 | 74 |  | FALSE | (add and edit are separat use cases, but tasks often do affect both, which is why they are put together for time evaluation)
UC CRUD activities | 3 | 17 | 3 | 1 | 24 |  | FALSE | (add and edit are separat use cases, but tasks often do affect both, which is why they are put together for time evaluation)
UC User Management | 8 | 8 |  | 2 | 18 |  | FALSE
UC Export / Copy Trip | 8 |  |  |  | 8 |  | FALSE | (copy and export are separat use cases, but tasks often do affect both, which is why they are put together for time evaluation)