## UC
Time spent on use cases
Project: Perfect Time - Plan Your Trip |  | YouTrack Report:
TINF17B2 |  | https://perfecttime.myjetbrains.com/youtrack/reports/time/145-1
UC | Documentation | Coding | Testing | Warm-Up time | Total | FP | Completed? | Remarks
UC Register / Login | 6 | 5 | 2 | 2 | 15 | 29.44 | TRUE
UC CRUD trips | 12 | 12 | 3 | 5 | 32 | 98.91 | FALSE | (view all trips and CRUD trips are separat use cases, but tasks often affect both, which is why they are put together for time evaluation)
UC CRUD locations | 8 | 32 | 6 | 28 | 74 | 75.44 | FALSE | (add and edit are separat use cases, but tasks often do affect both, which is why they are put together for time evaluation)
UC CRUD activities | 3 | 17 | 3 | 1 | 24 | 75.44 | FALSE | (add and edit are separat use cases, but tasks often do affect both, which is why they are put together for time evaluation)
UC User Management | 8 | 8 |  | 2 | 18 | 42.32 | FALSE
UC Export | 4 |  |  |  | 4 | 34.2 | FALSE
UC Copy Trip | 4 |  |  |  | 4 | 34.2 | FALSE
Time-FP-Evaluation
UC | FP | Time Total (/wo warm-up) | Time/FP
UC Register / Login | 29.44 | 13 | 0.44158
UC CRUD trips | 98.91 | 27 | 0.27298
UC CRUD locations | 75.44 | 46 | 0.60976
UC CRUD activities | 75.44 | 23 | 0.30488
Total Semester 1 | 279.23 | 109 | 0.39036
Schätzungen | FP | Time (estimated)
UC User Management | 42.32 | 20.2211
UC Export | 34.2 | 18.144
UC Copy Trip | 34.2 | 18.144
Total Semester 2 | 110.72 | 56.509