## Risk evaluation
Risk evaluation
Project: Perfect Time - Plan Your Trip
TINF17B2
Risk Name | Risk Description | Risk Probability of Occurrence (in %) | Risk Impact (1 low - 10 extreme) | Risk Factor | Risk Mitigation (Measures) | Person in Charge of Tracking (not person who brought it up!!)
Product fails to meet user requirements | The finished product cannot meet user expectation and demand, because - the user requirements have not been understood - the defined requirements did change during development - the developed product failed to meet the defined requirements | 18% | 10 | 1.8 | - check app market - check use cases against SRS - ensure tests cover the required functionality - focus on most significant / user functions first - get feedback from customer | Jan (Systems Analyst)
Underlying (web) technology changes and disables product | The product stops working, because - the injected dependencies changed and major product functions have to be adapted - the used web technolgie changes, and the product's architecture has to be adapted | 9% | 6 | 0.54 | - regularly update depencies - follow blogs on technology changes - make architecture easy to change - use state-of-the-art tech | Lukas (Software Architect)
Product quality is buggy and user satisfaction is low | The user experience is low, because the quality is low and buggy | 15% | 3 | 0.45 | - use automated testing - get user feedback before Go-Live - have a complete test coverage | Lea (Test Manager)
Product cannot be completed within the semester | The product cannot be completed until June, because - the project is to big for four people to handle - unexpected obstacles have hindered or delayed the completion - other subjects demand more time of the team members | 3% | 3 | 0.09 | - use time estimations - focus on most important functionality first - check for obstacles and use team work to remove them - talk to other professors | Tim (Process Engineer)
Senstitive user data is publically accessible | Stored user data is accessed without permission from external sources, because - the developed application has a vulnerability - the used technologies and platforms are accessible to others | 1% | 9 | 0.09 | - write a good impressum and terms of usage - check that used sources are reliable - update dependencies regularly | Lukas (Software Architect)
Team member leaves project | A team member leaves the project, because of - illness - leaving the company - leaving the course - changing the team | 0.5% | 2 | 0.01 | - team members should avoid leaving their company or their course - avoid dispute within the team - check in on team mates regularly | Lea (Project Manager)